## Ark1
|  | Week 1 Planning & preperations |  |  |  |  | Week 2 Design & development |  |  |  |  | Week 3 Integration & Refinement |  |  |  |  | Week 4 Testing & Launch
Lofthus frukt & saft |  | 2020-08-13 | 2020-08-14 | 2020-08-15 | 2020-08-16 | 2020-08-17 | 2020-08-20 | 2020-08-21 | 2020-08-22 | 2020-08-23 | 2020-08-24 | 2020-08-27 | 2020-08-28 | 2020-08-29 | 2020-08-30 | 2020-08-31 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06
Assigned to
Team meeting & Prospect planning | Whole team | 2020-08-13: Plan
Preperations and research | Whole team | 2020-08-14: Prep
Wireframe & Site structure | Frøydis | 2020-08-15: Wireframe
Back end Development | Vishal | 2020-08-20: Development
Back end Development & UI refinement | Frøydis & Vishal | 2020-08-28: Development and UI refinement
Testing and refinement | Whole team | 2020-09-04: Testing & Refinement
Presentation with customer - Strategy | Whole team | 2020-08-17: Presentation; 2020-09-06: LAUNCH
Presentation with customer - Design | Whole team | 2020-08-27: Presentation
Presentation with customer - Final product |  | 2020-09-04: Presentation
Back end preperations | Vishal | 2020-08-15: Backend prep
Design elements / Style tile | Frøydis | 2020-08-20: Design elements
Content integration | Frøydis | 2020-08-28: Content integration
Browser testing | Vishal | 2020-08-31: Browse test
Content writing / Seo | Julia | 2020-08-16: Content writing
Marketing planning | Jim | 2020-08-17: Marketing planning
TEAM & ROLES
Project Manager | Mike
Front-end Developer | Frøydis
Back-end Developer | Vishal
Content Manager | Julia
Marketing Manager | Jim